## collapse API
API | PARAMS |  | RESULT | EXPECTED | REMARKS
user_process_user | { "id": 817095, "collapse_by": "user_process_user" }
|  |  | FAILS | FAILS | NOT IMPLEMENTED
process_user | { "id": 817095, "collapse_by": "process_user" }
|  |  | WORKS | WORK | EDGE FILTERS OF LABEL ARENT GETTING APPLIED | FIXED @ 1640
user_process | { "id": 817095, "collapse_by": "user_process" } |  |  |  | Query fails as expected because 1st step is union step the bug which was identified yesterday. Basically the prev_view should here in corner case should be main but getting None. Also the 1st level is level1 it should not contain with clause. The 2nd step clause in union step uses the prev_view as local view of prev 2nd iter not top level view,
|  |  | QUERY FAILS | WORK |  | FIXED at 1530
user_email_user | { "id": 817095, "collapse_by": "user_email_user" } |  | WORKS | WORK | 0 result because all edges are of label edge
{ "id": 817095, "collapse_by": "user_URL_user" }
user_URL_user |  |  | QUERY FAILS | WORS | Because right tables for filtering on edge isn't joined in traversal when iteration = 1
FIXED @ 1720
| { "id": 817095, "collapse_by": "ip_user" } |  |  |  | Exception calling application: list index out of range
ip_user |  |  | CODE fails | WORKS | Query fails because the prev view for step1 in union isn't correct | FIXED @ 1800
|  |  | Query fails @ 1730 |  | I was executing the iterate step twice. Solves lot of problems. Once inside VCI step and once in ByteCodeExecutor
{ "id": 817095, "collapse_by": "process_ip" }
process_ip |  |  | WORKS | WORK | 0 result because all edges are of label edge
collapse_process_communicated |  |  | FAILS | FAILS | NOT IMPLEMENTED
process_downloaded_on | { "id": 817095, "collapse_by": "process_downloaded_on" }
|  |  | QUERY FAILS @ 1800 | WORK | Only Coalesce step, maybe not implemented the changes I just did in Union step to make only union work
The PREV_VEW is None, change we did for Union wasn’t implemented
When vertex label filter is applied, we need to use to use tbl prefix due to ambigous col name
FIXED @ 1810
| { "id": 817095, "collapse_by": "user_touched_host" } |  |  |  | Simple 1 hop traversal
|  |  | QUERY FAILS @ 1810 | WORK | When vertex label filter is applied, we need to use to use tbl prefix due to ambigous col name
user_touched_host |  |  |  |  | Fixed @ 1815
{ "id": 817095, "collapse_by": "collapse_host_user" }
collapse_host_user |  |  | WORKS | WORK | 0 result because all edges are of label edge
{ "id": 817095, "collapse_by": "collapse_user_clicked_url" }
collapse_user_clicked_url
|  |  | WORKS | WORK | 0 result because all edges are of label edge
collapse_user_url_process |  | NA
background_process |  | NA

## Others
New Handle | Old Handle |  | Params
getGraphForId | generate_graph |  | { "id": 817095, "dedup": "true" }
getGraphForId | date_filters | { "id": 817095, "dedup": "true", "startTime": "2020-07-30 9:30:00", "endTime": "2020-07-30 10:30:00", "direction": "out" }
getGraphForProperty | search_for | { "search_for": "ip", "search_value":"192.168.0.30", "dedup": "true", "startTime": "2020-07-30 9:30:00", "endTime": "2020-07-30 10:30:00", "direction": "out" }
NA | get_data_sources